## Slide 1: Communication Management
PMI Knowledge Areas

## Slide 2: Importance of Good Communications
Communication Paths Between a Project’s Parties-At-Interest

## Slide 3: Project Communications Management Processes
Planning Communications management
Managing communications
Controlling communications

## Slide 4: Keys to Good Communications
~80-90% of a PM’s time spent communicating
  Focus on needs – both group and individual
  Mix methods - formal and informal
  Set the stage for communicating bad news
Distribute important information in an effective and timely manner
Determine the number of communication channels

## Slide 5: Communications Channels
As the number of people involved increases, the complexity of communications increases because there are more communications channels or pathways through which people can communicate.
Number of communications channels = n(n-1)
2 where n is the number of people involved

## Slide 6: Communications Management Plan Contents
Stakeholder communications requirements
Suggested methods or technologies for conveying the information
Escalation procedures for resolving issues
Revision procedures for updating the communications management plan
A glossary of common terminology

## Slide 7: Sample Stakeholder Analysis for Project Communications

## Slide 8: Communication Technology Determination
Factors contributing to determining the communication technology to be used:
  Availability
  Project environment
  Project Length
  Urgency
  Preparation Level

## Slide 9: Importance of Face-to-Face Communication
Communication needs to be adjusted depending on the channel
How should you approach communication
Short, frequent meetings are often very effective in IT projects

## Slide 10: Communication Model

## Slide 11: Communication Model

## Slide 12: Executing Process Group: Managing Communications
Managing communications is a large part of a project manager’s job
Important considerations include:
  Technology
  Appropriate methods and media to use
  Performance reporting

## Slide 13: Distributing Information
Distribution Methods
Distribution Tools
Distribution of Information

## Slide 14: Classifications for Communication Methods
Interactive
Push
Pull

## Slide 15: Distributing Information in an Effective and Timely Manner
Don’t bury crucial information
Don’t be afraid to report bad information
Oral communication via meetings and informal talks helps bring important information—good and bad—out into the open

## Slide 16: Reporting Performance
Performance reporting keeps stakeholders informed about how resources are being used to achieve project objectives
  Status reports
  Progress reports
  Forecasts

## Slide 17: Monitor/Control Process Group: Controlling Communications
The main goal of controlling communications is to ensure the optimal flow of information throughout the entire project life cycle
The project manager and project team should use their various reporting systems, expert judgment, and meetings to assess how well communications are working.
  If problems exist, the project manager and team need to take action, which often requires changes to the earlier processes of planning and managing project communications

## Slide 18: Suggestions for Improving Project Communications
Develop better communication skills
Run effective meetings
Use e-mail and other technologies effectively
Use templates for project communications

## Slide 19: Developing Better Communication Skills
Most companies spend a lot of money on technical training for their employees, even when employees might benefit more from communications training
It takes leadership to improve communication

## Slide 20: Running Effective Meetings
Determine if a meeting can be avoided
Define the purpose and intended outcome of the meeting
Determine who should attend
Provide an agenda before meeting
Set the ground rules for the meeting

## Slide 21: Using E-Mail, Instant Messaging, Texting, and Collaborative Tools Effectively
Make sure that e-mail, instant messaging, texting, or collaborative tools are an appropriate medium for what you want to communicate
Be sure to authorize the right people to share and edit your collaborative documents

## Slide 22: Other Communication Considerations
Rarely does the receiver interpret a message exactly as the sender intended
Geographic location and cultural background affect the complexity of project communications
  Different working hours
  Language barriers
  Different cultural norms

## Slide 23: Using Templates for Project Communications
Many technical people are afraid to ask for help
Providing examples and templates for project communications saves time and money
Organizations can develop their own templates, use some provided by outside organizations, or use samples from textbooks
Recall that research shows that companies that excel in project management make effective use of templates

## Slide 24: Lessons Learned Reports & Archives
The project manager and project team members should each prepare a lessons-learned report
Project archives are a complete set of organized project records that provide an accurate history of the project
  These archives can provide valuable information for future projects as well

## Slide 25: Project Web Sites
Many project teams create a project Web site to store important product documents and other information
Microsoft’s Project Web Application Master Project Summary Screen

## Slide 26: Chapter Summary
Communication should run throughout the project. This is why the communication plan is so important.
  Goal: deliver the right information to the right people at the right time
The work performance measures communicated can have impacts throughout the knowledge areas including scope, time, cost and quality