## Slide 1: Procurement Management

## Slide 2: Importance of Project Procurement Management
Procurement means acquiring goods and/or services from an outside source
  Other terms include purchasing and outsourcing
Experts predict that global spending on computer software and services will continue to grow

## Slide 3: Why Outsource?
To access skills and technologies
To reduce both fixed and recurrent costs
To allow the client organization to focus on its core business
To provide flexibility
To increase accountability

## Slide 4: Contracts
A contract is a mutually binding agreement that obligates the seller to provide the specified products or services and obligates the buyer to pay for them
  Contracts can clarify responsibilities and sharpen focus on key deliverables of a project
  Because contracts are legally binding, there is more accountability for delivering the work as stated in the contract

## Slide 5: Project Procurement Management Processes
Project procurement management: Acquiring goods and services for a project from outside the performing organization
Processes include:
  Planning procurement management
  Conducting procurements
  Controlling procurements
  Closing procurements

## Slide 6: Planning Procurement Management
Identifying which project needs can best be met by using products or services outside the organization
Types of Contracts:
  Fixed Price (or lump sum)
  Cost Reimbursable
  Time and Material
  Unit Price

## Slide 7: Point of Total Assumption
The Point of Total Assumption (PTA) is the cost at which the contractor assumes total responsibility for each additional dollar of contract cost
  Contractors do not want to reach the point of total assumption, because it hurts them financially, so they have an incentive to prevent cost overruns
The PTA is calculated with the following formula:
PTA = (ceiling price – target price)/government share + target cost

## Slide 8: Cost Reimbursable Contracts
Cost plus incentive fee (CPIF)
Cost plus fixed fee (CPFF)
Cost plus percentage of costs (CPPC)

## Slide 9: Contract Clauses
Contracts should include specific clauses to take into account issues unique to the project
Can require various educational or work experience for different pay rights
Often includes:
  Termination clause
  Limitation of liability clause

## Slide 10: Tools and Techniques for Planning Purchases and Acquisitions
Expert judgment
Market research
Make-or-buy analysis: General management technique used to determine whether an organization should make or perform a particular product or service inside the organization or buy from someone else

## Slide 11: Contract Statement of Work (SOW)
A statement of work is a description of the work required for the procurement
  If a SOW is used as part of a contract to describe only the work required for that particular contract, it is called a contract statement of work

## Slide 12: Procurement Documents
Request for Proposals
  Proposal
Requests for Quotes
  Bid

## Slide 13: Source Selection Criteria
It’s important to prepare some form of evaluation criteria, preferably before issuing a formal RFP or RFQ
Beware of proposals that look good on paper; be sure to evaluate factors, such as past performance and management approach

## Slide 14: Conducting Procurements
Deciding whom to ask to do the work
Sending appropriate documentation to potential
sellers
Obtaining proposals or bids
Selecting a seller
Awarding a contract

## Slide 15: Approaches for Procurement
Organizations can advertise to procure goods and services in several ways:
  Approaching the preferred vendor
  Approaching several potential vendors
  Advertising to anyone interested

## Slide 16: Seller Selection
Organizations often do an initial evaluation of all proposals and bids and then develop a short list of potential sellers for further evaluation

## Slide 17: Controlling Procurements
Ensures that the seller’s performance meets contractual requirements
Contracts are legal relationships, so it is important that legal and contracting professionals be involved in writing and administering contracts
It is critical that project managers and team members watch for constructive change orders

## Slide 18: Suggestions for Change Control in Contracts
Evaluation of any change should include an impact analysis. How will the change affect the scope, time, cost, and quality of the goods or services being provided?
Changes must be documented in writing. Project team members should also document all important meetings and telephone phone calls

## Slide 19: Closing Procurements
The project team should:
    Determine if all work was completed correctly and satisfactorily
    Update records to reflect final results
    Archive information for future use
The contract itself should include requirements for formal acceptance and closure

## Slide 20: Tools to Assist in Contract Closure
Procurement audits identify lessons learned in the procurement process
Negotiated settlements help close contracts more smoothly
A records management system provides the ability to easily organize, find, and archive procurement-related documents

## Slide 21: Chapter Summary
Project procurement management involves acquiring goods and services for a project from outside the performing organization
Processes include:
  Plan procurement management
  Conduct procurements
  Control procurements
  Close procurements